## Slide 1: EVER HEALTH TECHNOLOGY PLAN
Presented by: Eagle Consulting

## Slide 2: EAGLE CONSULTING About Us
IT Consultancy and contracting agency for over 20 years
Founded in 1995
Goal of assisting businesses in staying up to date with the technological world around them
Acts as “Middle Man” for bringing close and personalized technology services to businesses in need

## Slide 3: EAGLE CONSULTING Mission
To stay up to date on current IT developments so that we may provide the most effective solution for your specific business needs
Aim to provide a fast, efficient, and most importantly effective IT answers
Save you time and money
Have a positive effect on the clientele you closely interact with

## Slide 4: EAGLE CONSULTING Vision
Facilitate an ever increasing amount of information technology solutions
Our desire is to constantly learn and develop new techniques
Aim is to be the best at understanding what makes your company special to provide the best information technology solution for you

## Slide 5: EVER HEALTH About Them
A chain of fitness centers operating nationwide 24/7
In 1973 two retired coaches, Henry Truman and Michael Hatch opened the first center in Columbus, Ohio
Prides itself not only on equipment and technology, but also an amazing atmosphere, a tradition of welcome, and unique experience found nowhere else
Their corporate location currently operates out of Columbus, Ohio

## Slide 6: EVER HEALTH Mission
Goal is to provide an environment that promotes accessibility to fitness equipment and knowledge to anyone that needs it
Aims to give you the tools necessary to start and maintain a healthy lifestyle
Maintaining a comfortable and welcoming experience

## Slide 7: EVER HEALTH ORGANIZATIONAL CHART
Jason Zander President & CEO
Lawrie Gaffney CFO
Patrick lliott VP Finance
Lola Jacobsen VP Accounting
Olivier Renaud Team Director
Spencer Lowe Regional Manager
Of 5 Locations
Mike Danselio Regional Manager
Of 5 Locations
Prashanth Desai Regional Manager
Of 5 Locations
Szabolcs Vajda Director of Human Resources
Jason Kozleski VP Human Resources
Pat Coleman VP Customer Svc
Gym Manager
Assistant Manager of Gym
HR representative

## Slide 8: EVER HEALTH - 15 LOCATIONS
East Coast
Philadelphia, PA
Arlington, VA
Midwest
Cincinnati, OH
Detroit, MI
Columbus, OH
Milwaukee, WI Chicago, IL
Dallas, TX
Houston, TX
Tucson, AZ
West Coast
Albuquerque, NM
Los Angeles, CA
San Francisco, CA
Denver, CO
Las Vegas, NV

## Slide 9: THE PROBLEM
Ever Health website is outdated and lacks any type of client functionality
All information is stored locally
Customers must travel to the gym location to renew or cancel their membership
Major hassles that affect customer retention rate

## Slide 10: THE COST
Ability to maintain and handle member information has become increasingly haphazard
Improper charges to cancelled or duplicate members cost both time and money to repair
In the past 2 years they have seen a 30% drop in customer membership renewal, resulting in a total loss of over $1,000,000
Customer satisfaction decreased 20% due to difficulties

## Slide 11: THE SOLUTION
A centralized Database:
  Shared across all gym locations
  With all appropriate documentation
A redesigned and fully functional website:
  Add functionality that allows customers to create, renew, update, or cancel their membership
  Connected directly to the database

## Slide 12: THE SOLUTION
A Front end Interface:
  Properly documented and useable by all employees
  Capable of pulling and updating information from the database
An accounting system capable of monitoring:
  General Ledger
  Accounts Receivable/Payable
  Balance Sheet, Profit/Loss Statements

## Slide 13: THE SOLUTION
Database, website, and network systems monitoring to ensure functionality
Develop and streamline system manual/training to ensure staff learn and understand the system
Cost/Benefit Analysis
Back up and Disaster Recovery plan

## Slide 14: PROJECT COMPLETION
Expected completion date: December 13th, 2016
Upon Completion of this project, we expect to see:
  A 50% increase in overall customer satisfaction
  An 80% increase in customer retention
  Potential to see increased revenue between $500,000 - $800,000
  A 10% increase in Membership sign ups yearly; 2,000 new customers bringing in $200,000 annually
  A 10% increase in employee efficiency

## Slide 15: Project Team Roles and Responsibilities
Roney Whonshevins Project Lead
Jacob Wagner Software Developer
Adan Maxamed Software Developer
James Leahy Web Developer
Guy Banaga Network Engineer
Andrew Butts Network Engineer

## Slide 16: IMPLEMENTED SYSTEM
Gym Clientele
Database
Gym Location

## Slide 17
2016
2016
Today
09/11
09/18
09/25
10/02
10/09
10/16
10/23
10/30
Eagles Consulting
10/31/2016
5 days
9/13/16 - 9/19/16
System Design
5 days
9/20/16 - 9/26/16
Creation of Financial System
5 days
9/27/16 - 10/3/16
Creation of Database Sytem
5 days
10/4/16 - 10/10/16
Excel Integration
5 days
10/11/16 - 10/17/16
Business Documents
5 days
10/18/16 - 10/24/16
Advertising Materials
5 days
10/25/16 - 10/31/16
Website Development
PROJECT TIMELINE

## Slide 18
2016
2016
Today
10/30
11/06
11/13
11/20
11/27
12/04
12/11
Eagles Consulting
12/12/2016
5 days
11/1/16 - 11/7/16
Report Creation
5 days
11/8/16 - 11/14/16
System Testing
5 days
11/15/16 - 11/21/16
Training
5 days
11/22/16 - 11/28/16
System Development Part 1
5 days
11/29/16 - 12/5/16
System Development Part 2
5 days
12/6/16 - 12/12/16
System Development Part 3
1 day
12/13/16
Presentation

## Slide 19: EVER HEALTH INTERVIEW SCHEDULE
GYM CEO – Jason Zander
  Location: CEO’s Office
  Time: Scheduled Appointment
  Questions:
    How do you feel your operation is running as of now? What parts of that do you think could be fixed with a new information system?
    What statement would you like this newly implemented system to make?
    What are your top priorities when it comes to the average member?
    What information would you like the new system to compile?
    What would the ideal situation of your business look like after the system has been implemented?

## Slide 20: EVER HEALTH INTERVIEW SCHEDULE
GYM MANAGERS – most profitable/least profitable locations
  Location: Local Gym Offices
  Time: Scheduled Day Appointment
  Questions:
    What day to day problems do you experience?
    What are the most common complaints that you experience?
    How do you feel your operation is running as of now? What parts of that do you think could be fixed with a new information system?
    What would the ideal, day to day situation of your business look like after the system has been implemented?

## Slide 21: EVER HEALTH INTERVIEW SCHEDULE
GYM MEMBERS – anonymous survey
  Location: N/A
  Time: N/A
  Questions:
    What do you feel that your gym handles well?
    What are the areas that the gym is lacking in?
    Would you prefer to register, renew, or cancel your membership online?
    What improvements would you like to see with the website?
    What information would you like available to you?

## Slide 22: Member Login

## Slide 23: Create Account

## Slide 24: Member Landing Page

## Slide 25: Change Password

## Slide 26: Employee Login

## Slide 27: Thank You!